PROJECT PROPOSAL

navari.com E-COMMERCE
DYNAMIC WEB PLATFORM

Migration to React & Node.js, Custom Admin Control Panel, Product & Order Management, Live Billing, Delivery Tracking & Automated WhatsApp API Integration

————————————————————————————————————————

| Prepared For: | Vastra Handloom Management |
| --- | --- |
| Project Budget: | Rs. 1,35,000/- INR (Fixed, All-Inclusive) |
| Project Timeline: | 30 - 45 Days (From Kickoff) |
| Primary Features: | Dynamic E-commerce, Admin Panel, Billing, Tracking & WhatsApp Alerts |
| Date of Proposal: | July 16, 2026 |

1. Executive Summary

Vastra Handloom is an exclusive online marketplace dedicated to promoting traditional handloom clothing and fabrics. The current storefront is a collection of static web pages (HTML, CSS, and Client-Side JS). While it displays products elegantly, it lacks the backend capabilities required to run an active retail business—such as dynamic catalog updates, interactive customer accounts, automated checkout, billing systems, inventory control, and order tracking.

This proposal details the transition of the Vastra Handloom website from static pages into a powerful, high-performance, dynamic web application built using the modern MERN Stack (React.js, Node.js, Express, and MongoDB). Furthermore, to streamline operations, a comprehensive Admin Control Panel will be built to handle products, billing, and orders, backed by automated WhatsApp Business API alerts to keep customers continuously informed of their orders.

The complete solution is structured to fit within a fixed budget of Rs. 1,35,000/- INR, which covers all development costs, production server hosting charges, database costs, and initial WhatsApp API integration with pre-loaded messaging credits. The deployment timeline is planned for 30 - 45 days.

2. Project Scope & Functional Modules

The project will be split into four core technical areas: Frontend Dynamic Migration, Backend Services, the Admin Control Panel, and automated Customer Engagement (WhatsApp API).

Module 2.1: Frontend Dynamic E-Commerce Application (React.js)

We will convert the existing HTML/CSS design templates of Vastra into a fully responsive React.js single-page application (SPA) or Server-Side Rendered pages for fast loading and SEO friendliness. Key frontend integrations include:

Dynamic Shop Page: Dynamic product rendering on the Shop Page (categorized and searchable).

Product Detail Page: Interactive Product Detail Page displaying real-time stock levels, dynamic images, and fabric details.

Cart & Wishlist: Fully operational Cart & Wishlist powered by client state management (persisted via LocalStorage/User Session).

Checkout Flow: Seamless Checkout Form validating shipping info, calculating discounts, and integrating with payment gateways.

User Authentication: Secure customer login/signup allowing order history retrieval and profile updates.

Module 2.2: Secured Backend API (Node.js & Express)

A highly robust and protected REST API will be built using Node.js and Express to drive the web application logic:

Role-Based Authentication: JSON Web Tokens (JWT) and HTTP-only cookies to verify user identities and roles (User vs. Admin).

Product APIs: APIs to fetch products with pagination, category filters, and search capabilities.

Order & Billing APIs: Endpoints for processing checkout, generating invoice records, and deducting stock quantities.

Delivery Tracking APIs: API endpoints mapping to tracking numbers and milestone statuses for live shipment updates.

Secure Architecture: Rate-limiting, payload validation, and CORS setup to prevent hacking, data scraping, or malicious requests.

Module 2.3: Database Infrastructure (MongoDB)

A robust database layer will be hosted on MongoDB Atlas, configured with replica sets for high availability and daily backups:

Product Schema: Includes product title, details, weavers, materials, price, discount, inventory counts, and image arrays.

User Schema: Structured to store buyer metadata, hashed passwords, contact details, and shipping/billing addresses.

Order & Invoice Schema: Records ordered items, final price, transaction IDs, tax, and order statuses (Pending, Processed, Shipped, Delivered).

Tracking Logs Schema: Maintains log history of delivery coordinates, tracking IDs, dispatch time, and estimated delivery dates.

Module 2.4: Admin Control Panel (Product, Order & Billing Management)

The administrative panel will act as the nerve center for Vastra's day-to-day business operations:

Product & Inventory Panel: Upload new products with multiple images, assign categories, and update stock counts instantly.

Order Management Panel: A unified screen listing all customer orders. Admins can view order details, change statuses, and cancel orders.

Billing & Invoicing: Generates digital bills/PDF invoices automatically upon order confirmation. Includes options for printing and manual invoice generation.

Delivery Tracker Management: A dedicated screen where the admin can input tracking details (Carrier Name, Tracking ID, Live Status URL) or manually click milestones to update the delivery status.

Module 2.5: WhatsApp Messaging Integration

To maximize customer satisfaction and reduce support queries, we will integrate WhatsApp Business API (via Meta Cloud API or an BSP like Twilio/WATI):

Order Confirmation Alert: Sent automatically to the customer's phone number as soon as their payment/order is successful.

Invoice & Packaging Alert: Sent once the shipment is packaged, including the generated PDF invoice and estimated delivery date.

Shipping & Live Tracking Alert: Triggered when the product is shipped, containing the tracking link and estimated delivery date.

Delivery Confirmation: Sent immediately when the package is delivered, thanking the customer and requesting product reviews.

3. Implementation Timeline & Milestones

The project will be completed in 30 to 45 Days. The milestone roadmap is divided as follows:

| Milestone / Phase | Key Deliverables | Timeline |
| --- | --- | --- |
| Phase 1: Database & System Design | • Finalizing tech stack configurations • MongoDB schema architecture and security rules design • High-level UI/UX wireframes for the Admin Panel | Days 1 - 7 |
| Phase 2: Node.js Backend Core Development | • Setup server repository, Express middleware, and security routes • Build product, cart, checkout, and invoice APIs • Configure PDF invoice generation engine | Days 8 - 18 |
| Phase 3: React Frontend & API Integration | • Convert static HTML/CSS files into structured React Components • Integrate global state management (cart, authentication, wishlist) • Connect client pages to Backend API services | Days 19 - 30 |
| Phase 4: Admin Dashboard & Delivery Modules | • Develop Admin Panel UI for product CRUD operations • Develop order review page with manual delivery tracker updates • Integrate invoice generation and download triggers for Admins | Days 31 - 38 |
| Phase 5: WhatsApp API Integration & Templates | • Setup Meta WhatsApp Cloud API credentials • Design and approve WhatsApp notification templates (Meta approvals) • Link backend event triggers (Order placed, shipped, tracking updated) | Days 39 - 42 |
| Phase 6: Testing, Deployment & Handover | • Conduct cross-browser testing and API security audits • Deploy React App to production and Node API to secure hosting VPS • Complete handover with documentation and admin walkthrough | Days 43 - 45 |

4. Costing & Infrastructure Allocation

The proposed costing is a fixed, all-inclusive budget of Rs. 1,35,000/- INR. This budget includes the complete development fees, live hosting servers, database instances, and WhatsApp messaging credits. No hidden charges will apply during the course of the project.

| Cost Category | Includes / Technical Details | Amount (INR) |
| --- | --- | --- |
| Platform Development Charges | • Dynamic React migration and Express.js REST API creation • Admin Dashboard (Product, Order, Invoicing, & Billing Panel) • Custom manual Delivery Tracker & logistics API mapping • Full system testing, UI polish, and deployment support | Rs. 1,10,000/- |
| Server & Database Charges (1-Year Hosting) | • Dedicated Linux VPS hosting Server • MongoDB Atlas secure Cloud database subscription • SSL certification, domain configuration, and automated backups | Rs. 15,000/- |
| WhatsApp API Setup & Messaging Credits | • WhatsApp Business API verification • Pre-loaded message template credits for customers • Integration with API Gateway | Rs. 10,000/- |
| TOTAL PROJECT COST | Inclusive of all development, hosting servers, cloud database, and WhatsApp messaging credits for initial period. | Rs. 1,35,000/- |

5. Technical Infrastructure Recommendations

To maintain stable operations under heavy traffic, we propose the following production infrastructure stack:

Frontend Hosting: React.js SPA with Client-Side Routing.  Hosted on a high-availability Virtual Private Server (VPS) , mapped to custom domains with SSH/SSL keys.

Backend Server Hosting: Node.js REST API with Express.js middleware. Hosted on a high-availability Virtual Private Server (VPS) , mapped to custom domains with SSH/SSL keys.

Database Hosting: MongoDB Atlas Shared/Dedicated Instance. Protected with SSL enforcement, IP Whitelisting, and secure environmental credentials.

WhatsApp Gateway:  WhatsApp templates pre-registered and approved by Meta Business Suite to ensure seamless bulk delivery without getting flagged.

6. Commercial Terms & Project Sign-Off

Milestone Payment Terms:

Advance Payment: 30% (Rs. 40,500/-) to initiate the system design, UI layouts, and MongoDB configuration.

Development Milestone: 30% (Rs. 40,500/-) upon backend API development completion and client review of API functionalities.

Integration Milestone: 30% (Rs. 40,500/-) upon frontend integration, Admin Control Panel completion, and initial WhatsApp template setups.

Deployment & Handover: 10% (Rs. 13,500/-) after successful UAT, production server deployment, domain mapping, and final handover.

Client Responsibilities:

Product Catalog: Providing all relevant handloom catalog information, fabric descriptions, and high-quality product images.

Meta Verification: Verifying Meta Business Manager account to activate official WhatsApp Business API numbers.

Post-Deployment Support:

We offer a 30-day post-launch support phase starting from the date of final production launch. This support period covers critical bugs, database configuration issues, server adjustments, and API monitoring. Annual maintenance contracts (AMC) for servers, WhatsApp credits, and database management can be renewed after 1 year.

| _______________________________ For Vastra Handloom Management | _______________________________ For Development Team / Partner |
| --- | --- |